## Sheet1
GANTT CHART
Deliverables | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 13 | Month 14 | Month 15
HOUSING STABILIZATION SERVICES (HSS)
Enrollment
If using NPI: Establish NPI via NPPES website | bar: Month 1
Identify staff who will be involved with enrollment process and determine who will submit provider enrollment application via the MPSE Portal located within MN-ITS | bar: Month 1
Prepare PDF provider enrollment forms | bar: Month 1
Gather signatures on PDF provider enrollment forms | bar: Month 1
Gather personal information from managing employees, owners, board members, officers, and trustees for disclosure of ownership or control interest purposes | bar: Month 1
Pay provider enrollment fee | bar: Month 1
Staff listed on DHS-3891 and other staff who will be providing HSS complete mandatory HSS trainings in TrainLink + Mandated Reporter Training | bar: Month 1
Complete provider enrollment within the MPSE Portal, including uploading PDF provider enrollment forms in the MPSE Portal, and submit provider enrollment application | bar: Month 1
After DHS completes initial provider enrollment application review: Follow instructions in return request letter to complete background studies in NetStudy 2.0 | bar: Month 2
After DHS completes initial provider enrollment application review: Correct any issues with application mentioned by DHS | bar: Month 2
Resubmit provider enrollment application with background study numbers | bar: Month 2
After HSS provider enrollment approval: Enroll with managed care organizations (MCOs) for billing | bar: Month 3
Project Setup
Select programs: Housing Consultation, Housing Sustaining, Housing Transition | bar: Month 1
Assign supervisor and hire housing case managers | bar: Month 1 to Month 5
Case manager training/onboarding | bar: Month 3 to Month 6
Develop referrals process | bar: Month 2 to Month 3
Establish/onboard EHR or other HIPAA compliant solution | bar: Month 1 to Month 6
Create program materials (intake forms, PA, etc.) | bar: Month 1 to Month 3
Develop policies and procedures manual | bar: Month 1 to Month 3
Assign point person and develop billing process | bar: Month 1 to Month 4
Implementation
Assign point person and develop revenue management process
MHCP Approval | bar: Month 3 to Month 15
Obtain PSN's and submit housing focused person centered plans | bar: Month 3 to Month 15
Provide and document HSS service | bar: Month 3 to Month 15
Submit claims, get paid, and follow revenue management process | bar: Month 4 to Month 15
Provide ongoing staff supervision, training, and quality assurance. | Month 7: Formal training; Month 10: Formal training; Month 13: Formal training
HOUSING SUPPORT
Enrollment
Obtain county or tribal agreement | bar: Month 1
Complete vendor profile form | bar: Month 2
Submit direct deposit form to DHS | bar: Month 2
Project Setup
Create program policies and manual | bar: Month 1 to Month 2
Setup financial tracking systems | bar: Month 1 to Month 3
Develop tracker and policies for pool funds | bar: Month 1 to Month 3
Develop program forms | bar: Month 1 to Month 3
Recruit staff for Housing Support | bar: Month 2 to Month 5
Setup forms and HS program in EHR | bar: Month 2 to Month 7
Setup billing in EHR | bar: Month 2 to Month 7
Enroll with HMIS | bar: Month 1 to Month 3
Landlord recruitment | Month 1: This will be ongoing
Establish billing process | bar: Month 1 to Month 5
Implementation
Complete program participant enrollment per HS contract | bar: Month 3 to Month 5
Start housing program participants/complete HS paperwork | bar: Month 4 to Month 15
Provide ongoing intensive case manager to program participants | bar: Month 4 to Month 15
Submit claims, get paid, and follow revenue management process | bar: Month 5 to Month 15
Provide ongoing staff supervision, training, and quality assurance. | bar: Month 5 to Month 15